## Sheet1
ID | Requirement description | Test | Passed | Learnings
Example | Completed system module will withstand vibrations up to 3g | Mount module of shock generator module capable of producing 3g | YES | The requirement initially specified only a g-value. However, the client expected the to test a frequency range up to 300Hz, and this did not come across completely during communications. Whilst the test was set up correctly for the requirement as-defined, and does allow the requirement to be tested, the shock-generator can only produce single-shocks and does not allow measurement of the frequency-dependent rejection of external vibrations. Therefore the test did not satisfy the clients original expectations.
Primary
R.2. | The drone shall be capable of hovering and flying | Apply power to motors, with both manual control and stabilised control with the drone able to liftoff and turn. | No | N/A
R.30 | The drone must power off after 30s of disconnection | Manually disconnect the drone and check if the Drone has powered off after 30s | Yes | The requirements specify that a manual disconnection should occur after 30 seconds. However, in manual command mode, this threshold should be reduced to a much shorter duration, typically less than one second. Complete verification of this behaviour was not possible, as the disconnection tests were conducted without the drone in flight. Consequently, the tests did not account for realistic operational conditions or associated safety considerations.
R.1. | The drone shall operate in an indoor area. | N/A | Yes | The drone is designed for indoor use with small motors, propellers, battery and propeller gaurds.
R.17. | The drone shall utilise shrouded propellers or dedicated propeller guards | Drop drone onto propeller shouds from 2m onto hard concrete to check for durability and ability to guard propellers against collisions | Yes | 2 m drops concentrate load at ring-arm roots, the first failures were that the shrouds printed too thin, resulting in snapping or bending. Increasing the wall to 2.0mm and printing ring supports improved survivability. Now survives impact with no bending, ensuring propeller clearance.
R.3. | The drone shall navigate without the use a Global Positioning System (GPS). | The drone must be able to show its orientation and altitude on a websocket using on onboard MPU. Display must be within 5% of true position (angle) after 3 minutes of hovering. | No | Gyro bias drift dominated the first 2 min occurrences, but it was not significant until after 2 minutes. WebSocket latency doesn’t affect the estimate, but confuses the display during sudden changes. True testing while the drone is hovering has not been conducted.
R.4. | The drone shall maintain a set hovering altitude during autonomous surveillance. | After a setpoint the drone should not deviate from that position by 20cm or 30cm with wind over the span of 30s | No | Without the stable liftoff this could not be tested.
R.14. | A manual override system shall be available to the user | After automatic hovering is engaged the drone must show that the manual override can be engaged consistantly over 30 test runs. | Yes | Override engaged successfully after every test run.
R.27. | The drone shall be able to autonomously land safely where battery levels are low. | See R.2. | No | N/A
R.24. | Any third-party software used for the drone control system must be open-source and freely available. | N/A | Yes | All software can be made available on a public github.
R.23. | The drone design shall remain in a budget of $350.00 | N/A | Yes | All purchases are tracked and the total costs should remain below $350
R.20. | The drone shall be capable of flight stabilisation | See R.2. | No | N/A
R.5. | The drone shall maintain a default altitude of between 1.2 and 1.3 metres above ground level while surveying an area | See R.2. | No | N/A
R.18. | The power supplied shall be via one 1S or 2S Li-Po battery with capacity up to 800mAh. | The drone must be able to run all functions and be powered by a 1/2S battery of 800mAh, and keep motors running for 3 minutes. | Yes | Margin is tight at 1S under peak load, have a brown-out logging; confirm connector/keying and reverse-polarity protection. Drone should be capable of flight under 1S battery
R.15. | The drone shall have a custom PCB design for the flight controller which includes sensors and power distribution. | The PCB is tested for consistent 3.3V on power rails, and signal integrity is to be maintained such that the ESP32 can read the sensor value accurately | Yes | Keep local decoupling near ESP32 and MPU. Maintain clean ground returns away from motor drivers, and isolate signal lines from noisy lines. Note I²C pull-ups and routing to prevent EMI-induced read errors.
R.21. | The drone shall be able to maintain stability under wind conditions and disturbances. | See R.2. | No | N/A
Additional
R.16. | The PCB shall include custom motor drivers | The motors should reflect the PWM outputted by the ESP32. The drivers should not produce enough noise to disturb signal lines | Yes | After setting software setting the PWM to different speeds, the motor reflects these changes. Adding 10 Ω gate resistors and close flyback diodes cut dV/dt ringing and small RC snubber across the motor removed residual spikes. Copper pours hold local temperatures < 80 °C. Ensured ESP32 EN/IO0 were decoupled from PWM edges to avoid boot glitches.
R.19. | The drone shall be able to fly for a minimum of 3 minutes. | See R.2. | No | N/A
R.28. | The surveillance camera shall stream the live camera feed. | Has not been tested/implemented | No | This feature can be implemented, but the hovering and flight stabilisation requirements were prioritised.
R.26. | The UI shall have a battery level monitoring system available for low battery levels. | Has not been tested/implemented | No | N/A
R.29. | The surveillance camera shall record video for playback | See R.28 | No | N/A
R.25. | The UI shall have an error diagnostic and feedback system. | After errors are manually triggered, the UI system should show the errors as well as other applicable system information. | Yes | Errors were reliably detected after inducing faults with timestamps and priorities (critical > warning. The errors are exported to serial/WebSocket helped debug. Clear human-readable labels mapped from codes. Allows for live user reactions to errors.
R.6. | The hovering altitude shall be adjustable prior to the drone beginning operation (between 0.5 and 2 metres) | See R.2. | No | N/A
A.R.2. | The required drone operational capabilities shall be powered with only one battery. | The drone must be able to run all functions and be powered by a single battery, and keep motors running for 3 minutes. | Yes | See R.18
A.R.4. | A comprehensive operation manual and user guide shall be provided to the client for understanding, usage and further development. | A manual and comprehensive use guide should be easily accessible and avaliable on GitHub and Teams | Yes | Github available to sync firmware and documentation, includes quick-start and common issues notes.
A.R.6. | Placement of the components on PCB shall minimise signal distortion and heating for accurate flight paths and predictable behaviour. | With all components operating on the PCB, signals should still be readable to the ESP32 with accuracy of 5% | Yes | Keep local decoupling near ESP32 and MPU. Maintain clean ground returns away from motor drivers, and isolate signal lines from noisy lines. Note I²C pull-ups and routing to prevent EMI-induced read errors.
A.R.7. | The drone shall have a visual indication (LED) or audible system that warns personnel during initiation of flight. | LEDs on board the drone should be visible from 0.5m away in a well lit room | Yes | LEDs are clearly visible in normal indoor lighting from 0.5m away. LEDs can be ajusted in brightness by increasing the PWM of the LED power signal.
A.R.8. | The drone shall alert on the UI in cases over overheating. | Has not been tested/implemented | No | N/A
A.R.9. | The drone shall have LEDs to show when it is in charging mode. | Has not been tested/implemented | No | N/A
A.R.10. | The drone shall have visual or UI indicators to show when it is powering down or when it is operating autonomously. | Has not been tested/implemented | No | This feature can be implemented, but the hovering and flight stabilisation requirements were prioritised.
[5 empty] | 50 | 50
[5 empty] | 60 | 40
[5 empty] | 50 | 50
[7 empty] | 50 | 50
[5 empty] | 75 | 25
[7 empty] | 60 | 40
[5 empty] | 50 | 50
[7 empty] | 50 | 50
[5 empty] | 20 | 80
[7 empty] | 70 | 30
[5 empty] | 90 | 10
[7 empty] | 50 | 50
[5 empty] | 40 | 60
[7 empty] | 20 | 80
[5 empty] | 50 | 50
[7 empty] | 90 | 10
[5 empty] | 15 | 85
[7 empty] | 40 | 60
[5 empty] | 80 | 20
[7 empty] | 20 | 80
[5 empty] | 20 | 80
[7 empty] | 50 | 50
[5 empty] | 50 | 50
[7 empty] | 15 | 85
[5 empty] | 80 | 20
[5 empty] | 55 | 45
[7 empty] | 80 | 20
[5 empty] | 785 | 715
[5 empty] | 0.91083 |  | 20 | 80
[7 empty] | 50 | 50
[7 empty] | 80 | 20
[7 empty] | 55 | 45
[7 empty] | 800 | 800
---
Note on A1: Instructions: Identifier for requirement
Note on B1: Instructions: Detailed statement of requirement
Note on C1: Instructions: Description of test that is used to validate that requirement has been met
Note on D1: Instructions: Did the design pass the test for this specific requirement YES or NO answer
Note on E1: Instructions: What has been learned in terms of: 1. Was the requirement defined correctly? i.e. did the client understand the same this as the group? 2. Was the requirement statement traceable? 3. Was the test set up correctly to assess this specfific requirement? 4. Other details of relevance
Note on H16: Sunny Guo (23345534):